## Script Grading
SCRIPTS STATUS PROGRESS (As on 23-July-2025)
08 PM SLOT
Sr. # | Title | Writer | Director | Total Episodes | Received Episodes | Script Completion (20-June) | Script Completion (23-July) | Script Completion Progress % | Nadeem | Salman | Imran | Final Average Score | Status (20th June) | Status (23rd July)
28 | Rabta | Saqlain Abbas |  | 26 | 8 | 30.77% | 31% | - | NA | 9.6 | NA | N/A | In Writing | -
29 | Deal | Zanjabeel Asim Shah |  | 26 | 9 | 34.62% | 38% | 3.385% | NA | 8.2 | NA | N/A | In Writing | -
17 | Khuda aur Muhabbat 4 | Hashim Nadeem |  | 26 | 12 | 46.15% | 46% | - | NA | 6.8 | NA | N/A | Production Planning - In Writing - Feedback need to discuss | -
16 | Baazi | Umera Ahmed |  | 26 | 21 | 80.77% | 81% | - | NA | 6 | NA | N/A | Production Planning - In Writing | -
9 | Muhafiz | Sadia Akhtar | Ali Faizan | 27 | 27 | 90% | 95% | 5% | NA | 9 | 6.6 | 7.8 | Pre Production - In Editing | -
10 | Sara Aapi | Saqlain Abbas Team | Asad Jabal | 26 | 14 | 53.85% | 69% | 15.15% | NA | 8.7 | 5.6 | 7.15 | Pre-Production - In Writing | -
26 | Kafir Dil/Sangdil | Adeel Razzaq |  | 30 | 13 | 43.33% | 43% | - | NA | NA | 4.4 | N/A | In Writing | -
11 | Zabt | Saima Akram Chaudhry |  | 26 | 26 | 100% | 100% | - | NA | 8.4 | 4.4 | 6.4 | Pre-Production | -
31 | Dushmani/Wirasat | Sameera Fazal |  | 30 |  |  |  |  | NA | NA |  | N/A | Contract done - Story Under Discussion/Development | -
32 | Khaie 2 | Saqlain Abbas |  | 30 |  |  |  |  | NA | NA |  | N/A | Story Under Discussion/Development | -
33 | Mannat Murad(2) | Nadia Akhtar |  | 26 |  |  |  |  | NA | NA |  | N/A | Story Under Discussion/Development | -
34 | Tu ne Deewana Banaya | Maha Malik |  | 26 |  |  |  |  | NA | NA |  | N/A | Story Under Discussion/Development | -
27 | Jung-e-Ishq | Imran Ashraf |  | 16 | 10 | 62.5% | 56% | -6.5% | 8.3 | 8 | NA | 8.15 | In Writing | -
18 | Gawahi | Madiha Shahid/Wajiha Sahar |  | 30 | 30 | 100% | 100% | - | 7.9 | 8.2 | 4.8 | 6.9667 | Script completed | -
20 | Agar Tum Sath Ho/Jub Tum Sath Thay | Sadia Akhtar |  | 30 | 30 | 100% | 100% | - | 6.3 | 6.8 | 6 | 6.3667 | Script completed | -
13 | Milkiyat | Erum Wasi Saima Wasi |  | 30 | 30 | 100% | 100% | - | 5 | 8.3 | 6.2 | 6.5 | Production Planning | -
12 | Ishq Akhri Hai Tu | Erum Wasi Saima Wasi |  | 30 | 30 | 100% | 100% | - | 4.6 | 6.8 | 4.8 | 5.4 | Production Planning | -
22 | Jogan | Seema Munaf |  | 26 | 26 | 80% | 80% |  | 4.2 | NA | 6 | 5.1 | Need to be Re-Edit | -
24 | Ab Kiya Karein | Syed Ali Moeen |  | 30 | 18 | 60% | 63% | 3% | 3.8 | 8.8 | 6 | 6.2 | In Writing | -
14 | Shehdaie/Tere Bin 2 | Saqlain Abbas |  | 30 | 27 | 90% | 90% | - | 3.3 | 9.1 | 7.4 | 6.6 | Production Planning - In Writing | -
21 | Mohabbat Ishq Iman | Qaisra Hayat |  | 30 | 30 | 100% | 100% | - | 3.3 | NA | 6 | 4.65 | Script completed | -
15 | Karwahat/Tujhay Isqh Ho Khuda Karay | Sameera Fazal |  | 30 | 29 | 96.67% | 90% | -6.667% | 3.3 | 7 | 4.8 | 5.0333 | Production Planning - In Editing | -
25 | Tapish | Rehana Aftab |  | 30 | 18 | 60% | 67% | 7% | 3.3 | 8.6 | 4.6 | 5.5 | In Writing | -
23 | Kahani Ek Muhabbat Ke | Samina Ejaz |  | 35 | 24 | 68.57% | 89% | 20.43% | 3.3 | NA | 3.4 | 3.35 | In Writing | -
19 | Shikayat | Rukhsana Nigar |  | 28 | 28 | 100% | 100% | - | 2.1 | 7.4 | 4.8 | 4.7667 | Script completed | -
| On-air Drama - 03 | Production Planning - 06 | Story Discussed & Approved - 00
| Project on Shoot - 04 | Script completed not on shoot - 04 | Story Under Discussion/ Development - 04
| Pre-Production - 03 | In Writing/Editing - 08
07/09 PM SLOT
Sr. # | Title | Writer | Director | Total Episodes | Received Episodes | Script Completion Percentage (20-June) | Script Completion Percentage (23-July) | Script Completion Progress Percentage | Soure A: Score out of 10 | Soure B: Score out of 10 | Soure C: Score out of 10 | Final Average Score | Status (20th July) | Status Change (23rd July)
10 | Iblees | Hina Huma Nafees | Saleem Ghanchi | 50 | 50 | 100% | 100% | - | NA | NA |  | #VALUE! | In Pre-Production | Project is on Shoot
11 | Jurm e Wafa | Naila Zehra Jafri | Promax Media | 50 | 50 | 100% | 100% | - | NA | NA |  | #VALUE! | In Pre-Production - Outsoure | -
12 | Yar-e-Man/Betaab | Sidra Sehar Imran |  | 100 (20 minutes) | 100 (20 minutes) | 100% | 100% | - | 3.8 | NA |  | #VALUE! | Script completed | -
13 | Shatranj | Hina Huma Nafees |  | 35 | 35 | 100% | 100% | - | 5 | 7.2 |  | 4.0667 | Script completed | -
14 | Jhansa | Imran Syfer (5-50 Eps)/ Syed Ali Moeen (1-4 Eps) |  | 50 | 50 | 100% | 100% | - | 5.4 | 7.4 |  | 4.2667 | Script completed | -
15 | Banjaran | Samina Ejaz |  | 50 | 50 | 100% | 100% | - | 5.8 | NA |  | #VALUE! | Script completed | -
16 | Laut Aao Na | Rahat Jabeen |  | 31 | 31 | 100% | 100% | - | 7.1 | NA |  | #VALUE! | Script completed | -
17 | Nadan | Samra Bukhari |  | 50 | 33 | 66% | 62% | 4% | 3.8 | 7.6 |  | 3.8 | In Writing & Editing | -
18 | Sarmaya | Shabnam Sami Sani |  | 50 | 17 | 34% | 34% | - | NA | 7.4 |  | #VALUE! | In Writing | -
19 | BeMahar | Fiza Anwar |  | 26 | 3 | 11.54% | - | - | NA | NA |  | #VALUE! | In Writing | -
20 | Dhadkan/Dhanak | Imran Ali Syfer |  | 50 | 3 | 6% | 12% | 6% | NA | NA |  | #VALUE! | In Writing | -
21 | Girya Gar | Mounam Majeed |  | 26 | 8 | 30.77% | 31% | - | NA | 4.6 |  | #VALUE! | In Writing | -
22 | Afat 2/Mujhay Tum Se Muhabbat Hay | Soofia Khurram |  | 50 | 6 | 12% | 12% | - | NA | NA |  | #VALUE! | In Writing | -
23 | Wajood | Shafia Khan |  | 30 | 5 | 16.67% | 17% | - | NA | NA |  | #VALUE! | In Writing | -
24 | Aasaib Zada | Syed Nabeel/Shahid Nizami |  | 30 |  |  |  |  | NA | NA |  | #VALUE! | Story Discussed & Approved | -
25 | Ajnabi | Nuzhat Saman |  | 50 |  |  |  |  | NA | NA |  | #VALUE! | Story Discussed & Approved | -
26 | Bajjo - 2 | Javeria Saud |  | 50 |  |  |  |  | NA | NA |  | #VALUE! | Story Discussed & Approved | -
27 | Do Dil | Mansoor Ahmed Khan |  | 50 |  |  |  |  | NA | NA |  | #VALUE! | Story Discussed & Approved | -
28 | Bewafa | Erum Wasi Saima Wasi |  | 30 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
29 | Sarphira Ishq | Erum Wasi Saima Wasi |  | 30 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
30 | Muqadar Ka Likkha | Muhammad Anas | [6 empty] | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
31 | Pichal Peri | Amtul Aziz |  | 30 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
32 | Muhabbat Rooth Jaye Tou | Zeeshan Junaid | [6 empty] | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
33 | Dil e Rah Guzar | Saira Arif |  | 50 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
34 | Dil e Rawaan | Sarah Majeed |  | 30 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
35 | Zehreeli | Nighat Imran |  | 50 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
36 | Tu Jo Nahee | Irfan Aslam |  | 50 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
37 | Doraha | Rida Bilal |  | 30 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
38 | Meri Duniya | Edison Idrees Masih |  | 30 |  |  |  |  | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
39 | Bunty | Saqlain Team | [6 empty] | NA | NA |  | #VALUE! | Story Under Discussion/Development | -
SUMMARY
| On-air Drama - 03 | Production Planning - 00 | Story Discussed & Approved - 04 |  | NEW
| Project on Shoot - 06 | Script completed not on shoot - 05 | Story Under Discussion/ Development - 12
| Pre-Production - 02 | In Writing/Editing - 07
SPECIAL TELEILM PROJECTS
Sr. # | Title | Writer | Director | Total Episodes | Received Episodes | Script Completion Percentage (20-June) | Script Completion Percentage (23-July) | Script Completion Progress Percentage |  |  |  |  | Status (20th July) | Status Change (23rd July)
1 | Capt. Asfandyar Shaheed |  | ISPR Telefilm | ------ | ------ | 100% | 100% | - |  |  |  |  | Pre Production | Telefilm is on shoot
2 | Mere Abbu | Saira Arif | Father's Day | ------ | ------ | 100% | 100% | - |  |  |  |  | Script Final
3 | Good bye Pakistan | Adeel Razzaque | 14th August | ------ | ------ | 100% | 100% | - |  |  |  |  | Script Final
4 | Watan ki matti | Saira Arif | 6th September | ------ | ------ | 100% | 100% | - |  |  |  |  | Script Final
5 | Duniya Ko Bata do | Nooran Makhdoom | Branded Content | ------ | ------ | 100% | 100% | - |  |  |  |  | Script Final
6 | Dil Pasand | Imran Nazir | Eid Special Telefilm | ------ | ------ | 100% | 100% | - |  |  |  |  | Script Final
7 | God Father | Likhari | Eid Special Telefilm | ------ | ------ | 75% | 75% | - |  |  |  |  | Revised script is awaited
8 | Qubool Hai | Nighat Imran | Eid Special Telefilm | ------ | ------ | 75% | 75% | - |  |  |  |  | Script is in Editing Process
9 | Ghar Ke Naa Ghaat Ke | Amber Azhar | Eid Special Telefilm | ------ | ------ | 75% | 75% | - |  |  |  |  | Script is in Editing Process
10 | Tweet The Hearts | Soofia Khurrum | Eid Special Telefilm | ------ | ------ | [7 empty] | Script Received/Not Final
11 | Jhooti Farebi | Saira Raza | Eid Special Telefilm | ------ | ------ | [7 empty] | Script Received/Not Final
12 | Qismat Connection | Nida Hasnain | Eid Special Telefilm | ------ | ------ | [7 empty] | Script Received/Not Final
13 | Love by Chance | Nighat Imran | Eid Special Telefilm | ------ | ------ | [7 empty] | Script Received/Not Final
| On-air Drama |  | Script completed
| Project on Shoot |  | In Writing/Editing
| Pre-Production |  | Story Discussed & Approved
| Production Planning |  | Story Under Discussion/Development

## TOP 5 individual grading
TOP 5 PROJECTS WITH AGGREGATE SCORES OF ALL 3 EVALUATIONS
SR | TITLE | WRITER | COMPLETION | NADEEM | SALMAN | IMRAN | AVERAGE | STATUS
1 | Jung-e-Ishq | Imran Ashraf | 56% | 8.3 | 8 | NA | 8.15 | In Writing
2 | Muhafiz | Sadia Akhtar | 95% | NA | 9 | 6.6 | 7.8 | Pre Production - In Editing
3 | Sara Aapi | Saqlain Abbas Team | 69% | NA | 8.7 | 5.6 | 7.15 | Pre-Production - In Writing
4 | Gawahi | Madiha Shahid/ Wajiha Sahar | 100% | 7.9 | 8.2 | 4.8 | 6.97 | Script completed
5 | Shehdaie/Tere Bin 2 | Saqlain Abbas | 90% | 3.3 | 9.1 | 7.4 | 6.6 | Production Planning - In Writing
SALMAN's TOP 5 RATED
SR | TITLE | WRITER | COMPLETION | NADEEM | SALMAN | IMRAN | AVERAGE | STATUS
1 | Rabta | Saqlain Abbas | 31% | NA | 9.6 | NA | N/A | In Writing
2 | Shehdaie/Tere Bin 2 | Saqlain Abbas | 90% | 3.3 | 9.1 | 7.4 | 6.6 | Production Planning - In Writing
3 | Muhafiz | Sadia Akhtar | 95% | NA | 9 | 6.6 | 7.8 | Pre Production - In Editing
4 | Ab Kiya Karein | Syed Ali Moeen | 63% | 3.8 | 8.8 | 6 | 6.2 | In Writing
5 | Sara Aapi | Saqlain Abbas Team | 69% | NA | 8.7 | 5.6 | 7.15 | Pre-Production - In Writing
IMRAN GREEN's TOP 5 RATED
SR | TITLE | WRITER | COMPLETION | NADEEM | SALMAN | IMRAN | AVERAGE | STATUS
1 | Shehdaie/Tere Bin 2 | Saqlain Abbas | 90% | 3.3 | 9.1 | 7.4 | 6.6 | Production Planning - In Writing
2 | Muhafiz | Sadia Akhtar | 95% | NA | 9 | 6.6 | 7.8 | Pre Production - In Editing
3 | Milkiyat | Erum Wasi Saima Wasi | 100% | 5 | 8.3 | 6.2 | 6.5 | Production Planning
4 | Jogan | Seema Munaf | 80% | 4.2 | NA | 6 | 5.1 | Need to be Re-Edit
5 | Mohabbat Ishq Iman | Qaisra Hayat | 100% | 3.3 | NA | 6 | 4.65 | Script completed
6 | Ab Kiya Karein | Syed Ali Moeen | 63% | 3.8 | 8.8 | 6 | 6.2 | In Writing
7 | Agar Tum Sath Ho/ Jub Tum Sath Thay | Sadia Akhtar | 100% | 6.3 | 6.8 | 6 | 6.3667 | Script completed
NADEEM ASAD's TOP 5 RATED
SR | TITLE | WRITER | COMPLETION | NADEEM | SALMAN | IMRAN | AVERAGE | STATUS
1 | Jung-e-Ishq | Imran Ashraf | 56% | 8.3 | 8 | NA | 8.15 | In Writing
2 | Gawahi | Madiha Shahid/Wajiha Sahar | 100% | 7.9 | 8.2 | 4.8 | 6.9667 | Script completed
3 | Agar Tum Sath Ho/ Jub Tum Sath Thay | Sadia Akhtar | 100% | 6.3 | 6.8 | 6 | 6.3667 | Script completed
4 | Milkiyat | Erum Wasi Saima Wasi | 100% | 5 | 8.3 | 6.2 | 6.5 | Production Planning
5 | Ishq Akhri Hai Tu | Erum Wasi Saima Wasi | 100% | 4.6 | 6.8 | 4.8 | 5.4 | Production Planning
Projects appearing in at least 2 lists
Shehdai/ Tere Bin 2
Muhafiz
Ab Kia Karain
Milkiyat
Agar Tum Sath Ho / Jab Tum sath they
SR | TITLE | WRITER | COMPLETION | NADEEM | SALMAN | IMRAN | AVERAGE | STATUS
1 | Shehdaie/Tere Bin 2 | Saqlain Abbas | 90% | 3.3 | 9.1 | 7.4 | 6.6 | Production Planning - In Writing
2 | Muhafiz | Sadia Akhtar | 95% | NA | 9 | 6.6 | 7.8 | Pre Production - In Editing
3 | Ab Kiya Karein | Syed Ali Moeen | 63% | 3.8 | 8.8 | 6 | 6.2 | In Writing
4 | Milkiyat | Erum Wasi Saima Wasi | 100% | 5 | 8.3 | 6.2 | 6.5 | Production Planning
5 | Agar Tum Sath Ho/ Jub Tum Sath Thay | Sadia Akhtar | 100% | 6.3 | 6.8 | 6 | 6.3667 | Script completed